## TC Overview
DAILY AVERAGE
NB de cas à executer par jour | 130 | 257
RETARD / AVANCE
DATE | BACKLOG | DONE | PASSED | FAILED | BLOCKED | NOT APPLICABLE | IDEAL | PROJECTION | GLOBAL | DAILY
2019-10-01 | 7659 | 139 | 133 | 6 | 0 | 2 | 7659 | 7659 | 0 | 9
2019-10-02 | 7520 | 417 | 405 | 12 | 3 | 14 | 7529 | 7520 | 9 | 287
2019-10-03 | 7103 | 272 | 249 | 23 | 4 | 30 | 7399 | 7103 | 296 | 142
2019-10-04 | 6831 | 305 | 293 | 12 | 60 | 22 | 7269 | 6831 | 438 | 175
2019-10-07 | 6526 | 174 | 134 | 40 | 10 | 20 | 7139 | 6526 | 613 | 44
2019-10-08 | 6352 | 235 | 184 | 51 | 4 | 24 | 7009 | 6352 | 657 | 105
2019-10-09 | 6117 | [5 empty] | 6879 | 6117 | 762
2019-10-10 | [6 empty] | 6749 | 5860
2019-10-11 | [6 empty] | 6619 | 5603
2019-10-14 | [6 empty] | 6489 | 5346
2019-10-15 | [6 empty] | 6359 | 5089
2019-10-16 | [6 empty] | 6229 | 4832
2019-10-17 | [6 empty] | 6099 | 4575
2019-10-18 | [6 empty] | 5969 | 4318
2019-10-21 | [6 empty] | 5839 | 4061
2019-10-22 | [6 empty] | 5709 | 3804
2019-10-23 | [6 empty] | 5579 | 3547
2019-10-24 | [6 empty] | 5449 | 3290
2019-10-25 | [6 empty] | 5319 | 3033
2019-10-28 | [6 empty] | 5189 | 2776
2019-10-29 | [6 empty] | 5059 | 2519
2019-10-30 | [6 empty] | 4929 | 2262
2019-10-31 | [6 empty] | 4799 | 2005
2019-11-01 | [6 empty] | 4669 | 1748
2019-11-04 | [6 empty] | 4539 | 1491
2019-11-05 | [6 empty] | 4409 | 1234
2019-11-06 | [6 empty] | 4279 | 977
2019-11-07 | [6 empty] | 4149 | 720
2019-11-08 | [6 empty] | 4019 | 463
2019-11-11 | [6 empty] | 3889 | 206
2019-11-12 | [6 empty] | 3759 | 0
2019-11-13 | [6 empty] | 3629 | 0
2019-11-14 | [6 empty] | 3499 | 0
2019-11-15 | [6 empty] | 3369 | 0
2019-11-18 | [6 empty] | 3239 | 0
2019-11-19 | [6 empty] | 3109 | 0
2019-11-20 | [6 empty] | 2979 | 0
2019-11-21 | [6 empty] | 2849 | 0
2019-11-22 | [6 empty] | 2719 | 0
2019-11-25 | [6 empty] | 2589 | 0
2019-11-26 | [6 empty] | 2459 | 0
2019-11-27 | [6 empty] | 2329 | 0
2019-11-28 | [6 empty] | 2199 | 0
2019-11-29 | [6 empty] | 2069 | 0
2019-12-02 | [6 empty] | 1939 | 0
2019-12-03 | [6 empty] | 1809 | 0
2019-12-04 | [6 empty] | 1679 | 0
2019-12-05 | [6 empty] | 1549 | 0
2019-12-06 | [6 empty] | 1419 | 0
2019-12-09 | [6 empty] | 1289 | 0
2019-12-10 | [6 empty] | 1159 | 0
2019-12-11 | [6 empty] | 1029 | 0
2019-12-12 | [6 empty] | 899 | 0
2019-12-13 | [6 empty] | 769 | 0
2019-12-16 | [6 empty] | 639 | 0
2019-12-17 | [6 empty] | 509 | 0
2019-12-18 | [6 empty] | 379 | 0
2019-12-19 | [6 empty] | 249 | 0
2019-12-20 | [6 empty] | 119 | 0
2019-12-23 | [6 empty] | 0 | 0
2019-12-24 | [6 empty] | 0 | 0
| BACKLOG | TOTAL DONE
| 7659 | 1542

## Auto Overview
|  | Environnement1 : Mysql | [8 empty] | Environnement 2: Postgresql
| DATE | ECMS | Social | PLF | Wiki | Chat | Forum | Gatein | Task | Calendar | ECMS | Social | PLF | Wiki | Chat | Forum | Gatein | Task | Calendar
5.3.0-RC01 | 2019-10-01 |  |  |  |  | TC passed: 51 TC failed docker:4 Durée: 1h46 |  | TC passed: 28 TC failed docker:2 Durée:19mn | TC passed: 11 TC failed Docker:2 Durée: 11mn
| 2019-10-02 |  |  | TC passed: 62 TC failed docker:16 Durée: 1h20 Verification machine: ok | Funct passed133 Durée: 3h40
| 2019-10-03 | [8 empty] | TC sniff passed 23 TC sniff failed Doc: 57 Durée: 1h Vérification manuelle:4h
| 2019-10-04 | TC sniff passed: 119 TC failed docker: 12 Durée: 2h30 | TC funct passed: 51 TC failed docker:35 Durée: 2h VM: OK: 3h |  |  |  | TC sniff passed: 66 TC failed docker: 6 Durée exec: 1h20 VM: OK: 1h
5.3.0-RC02 | 2019-10-07 | TC smoke passed: 11 TC failed docker: 1 Durée: 15mn | TC smoke passed: 16 TC failed docker: 1 Durée: 29mn |  | Sniff passed82 Durée: 2h30 | [10 empty] | Sniff passed 71 Sniff failed : 0 Durée:1h20
| 2019-10-08 | [10 empty] | Snif passed:324 Failed docker:35 Durée: 10h18 | Passed: 64 Failed docker:14 Durée: 1h20 Verification ok |  | TC passed: 52 Failed docker:3 Durée: 1h46
2019-10-09
2019-10-10
2019-10-11
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-28
2019-10-29
2019-10-30
2019-10-31
2019-11-01
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-23
2019-12-24

## Ressources in TC
Date \Ressources | Devsquad1 | Devsquad2 | Ikram | Dorra | EXT. Hatem | EXT. Taha | Taha | Islem | Nesrine | Farouk
2019-10-01 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3
2019-10-02 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 8 | 3 | 8
2019-10-03 | 8 | 8 | 8 | 7 | 8 | 8 | 8 | 0 | 5 | 7
2019-10-04 | 8 | 8 | 8 | 7 | 8 | 6 | 8 | 0 | 3 | 0
2019-10-07 |  | 0 |  |  | 8 | 8 | 8 | 0 | 3 | 2
2019-10-08 |  | 8 |  |  |  |  | 8 |  |  | 2
2019-10-09
2019-10-10
2019-10-11
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-28
2019-10-29
2019-10-30
2019-10-31
2019-11-01
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-23
2019-12-24

## Macro planning
Month | oct |  |  |  | Nov |  |  |  | Dec
Week | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51
PLF version | RC1 | RC2 | RC3 | RC4 | RC5 | RC6 | RC7 | RC8 | RC9 | RC10 | RC11 | GA
R1 | FQA | FQA | FQA mobile | AD | FQA | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | ?
R2 | FQA | FQA mobile | LDAP | FQA | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | FQA | ?
R3 | FQA | FQA | FQA mobile | FQA | Cluster | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | ?
R4 | FQA | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | FQA | ?
R5 | Test auto + upgrade | auto + closing RC1 | auto + closing RC2 | auto + closing RC3 | auto + upgrade+ closing RC4 | auto + closing RC5 | auto + closing RC6 | auto + closing RC7 | auto + closing RC8 | auto + closing RC9 | auto + upgrade + closing RC10 | ?
R6 | FQA | FQA | FQA | FQA mobile | FQA | SSO | FQA mobile | FQA | FQA | FQA mobile | ? | ?
R7 | FQA | FQA | FQA | FQA mobile | FQA | FQA | FQA mobile | FQA | FQA | FQA mobile | ? | ?
TQA | Tomcat Standalone 1ere passe | Tomcat cluster 1ere passe | Test fixes | Test fixes | Test fixes | Test fixes | Test fixes? | Test fixes? | Test fixes? | Test fixes? | Test fixes?
Environnements Planifiés |  |  | AD | LDAP | Cluster | SSO
Prévisionnel ITOP |  |  | LDAP | Cluster | AD | SSO

## Test Cases priority
sub module |  | Story points | real | Historique tests 5.2.0 | BV guild architectes | BV guild analystes | Difference | BV moyen | Assignee | Status
Kill shindig |  | 9 | 9 |  | 100 | 100 |  | 100 | Farouk | OK
Gamification |  | 23 | 92 |  | 100 | 100 | 0 | 100 | Farouk | Blocked
Home page activity stream |  | 189 | 191 |  | 100 | 100 | 0 | 100 | Ikram | OK
Perk store |  | 18 | 49 | Non testé | 100 | 100 | 0 | 100 | Hatem | Blocked | Calendar
Kudos |  | 8 | 10 | Non testé | 100 | 100 | 0 | 100 | Hatem | Blocked | ECMS
Wallet |  | 77 | 86 | Non testé | 100 | 100 | 0 | 100 | Hatem | Blocked | Forum
Reward |  | 22 | 23 |  | 100 | 100 | 0 | 100 | Hatem | Blocked | GateIn
| Space template | 87 | 98 |  | 100 | 100 | 0 | 100 | Nesrine | In progress | PLF
Company branding |  | 37 | 38 |  | 100 | 90 | 10 | 95 | Taha | OK | Chat
People | find connection | 21 | 21 |  | 90 | 100 | 10 | 95 | Islem | In proress
Space | Appl management | 106 | 106 |  | 90 | 100 | 10 | 95 | Dorra | In progress
Mobile |  | 5357 | 1847 | Aléatoire | 90 | 100 | 10 | 95 | Farouk | In progress
Notifications | Mobile push notif | 134 | 134 |  | 80 | 100 | 20 | 90 | Dorra | In progress
People | User profile | 136 | 136 |  | 90 | 90 | 0 | 90 | Dev2:Samir | OK
Space | Space admin | 39 | 39 |  | 90 | 90 | 0 | 90 | Taha | In progress
Space | Space info | 58 | 32 |  | 90 | 90 | 0 | 90 | Ext. Hatem | OK
Space | Space management | 102 | 106 |  | 90 | 90 | 0 | 90 | Taha | OK
Space | activities | 62 | 62 |  | 90 | 90 | 0 | 90 | Dev1: Khouloud | OK
People | Activities | 647 | 651 |  | 90 | 80 | 10 | 85 | Farouk | In progress (100cases done)
People | My connection | 42 | 65 |  | 90 | 80 | 10 | 85 | EXT. Taha | OK
Regression |  | 10 | 10 |  | 90 | 80 | 10 | 85
Home page gadgets |  | 130 | 165 | Non testé | 70 | 90 | 20 | 80 | EXT. Hatem | In progress
Space | Member management | 83 | 90 |  | 90 | 70 | 20 | 80 | Dev1: Khouloud | In progress
Improve create event |  | 84 | 0 |  | 70 | 80 | 10 | 75
Regression |  | 136 | 136 |  | 70 | 80 | 10 | 75
Document upload |  | 4 | 4 |  | 80 | 70 | 10 | 75
Unified search |  | 166 | 166 |  | 90 | 60 | 30 | 75 | EXT. Taha | In progress
Notifications | Email | 195 | 195 |  | 80 | 70 | 10 | 75 | Ikram | In progress
Notifications | Intranet | 131 | 131 |  | 80 | 70 | 10 | 75
Notifications | Administration | 14 | 14 |  | 80 | 70 | 10 | 75 | Nesrine | In progress
Notifications | Settings | 5 | 5 |  | 80 | 70 | 10 | 75 | Nesrine | In progress
Notifications | Properties | 4 | 4 |  | 80 | 70 | 10 | 75 | Nesrine | In progress
Notifications | link to originating app | 27 | 27 |  | 80 | 70 | 10 | 75 | Nesrine | Open
Regression |  | 35 | 35 |  | 80 | 70 | 10 | 75
Navigation | Left navigation | 37 | 37 |  | 60 | 80 | 20 | 70
No regression test |  | 3 | 3 |  | 60 | 80 | 20 | 70
Event |  | 217 | 217 |  | 70 | 60 | 10 | 65
Navigation | Top navigation | 149 | 149 |  | 40 | 90 | 50 | 65 | Ikram | In progress
Autentfication with social network |  | 44 | 44 | Non testé | 70 | 60 | 10 | 65
Trial |  | 39 | 39 |  | 80 | 50 | 30 | 65
Security |  | 45 | 45 |  | 70 | 60 | 10 | 65
Document preview | Preview | 124 | 124 |  | 70 | 50 | 20 | 60
Administration |  | 24 | 24 |  | 20 | 100 | 80 | 60 | Islem | Open
Cluster | Basic | 119 | 119 |  | 10 | 30 | 20 | 60 |  |  | Forum | 703
Mongo Cluster |  | 3 | 0 |  | 10 | 10 | 0 | 60 |  |  | Social(MOB) | 1847
AD |  | 47 | 47 |  | 30 | 40 | 10 | 60 |  |  | Task | 161
LDAP |  | 97 | 97 |  | 30 | 30 | 0 | 60 |  |  | Wiki | 439
SSO |  | 34 | 34 |  | 30 | 40 | 10 | 60
Basic action |  | 43 | 43 | Non testé | 50 | 60 | 10 | 55
Copy of default folder |  | 7 | 7 |  | 50 | 60 | 10 | 55
Document Versionning |  | 116 | 116 |  | 50 | 60 | 10 | 55
Disable user |  | 90 | 0 | Non testé | 40 | 70 | 30 | 55
Space | Navigation mangement | 128 | 128 |  | 60 | 50 | 10 | 55
Activities |  | 73 | 73 |  | 60 | 40 | 20 | 50
Manage calendar |  | 114 | 114 |  | 70 | 30 | 40 | 50
Authentication |  | 4 | 4 |  | 50 | 50 | 0 | 50
Document preview | Comment | 66 | 66 |  | 60 | 40 | 20 | 50
Document preview | Display area | 96 | 96 |  | 60 | 40 | 20 | 50
Document preview | ECMS rendering | 4 | 4 |  | 60 | 40 | 20 | 50
Share document |  | 84 | 84 |  | 60 | 40 | 20 | 50
Site explorer | Admin | 301 | 301 | Non testé | 40 | 60 | 20 | 50
Site explorer | Collaboration | 67 | 67 | Non testé | 40 | 60 | 20 | 50
Site explorer | Info | 43 | 43 | Non testé | 40 | 60 | 20 | 50
Site explorer | Open in office | 211 | 211 |  | 90 | 10 | 80 | 50
Site explorer | Other check | 66 | 66 | Non testé | 40 | 60 | 20 | 50
Site explorer | Publication | 20 | 20 |  | 60 | 40 | 20 | 50
Autentificate |  | 39 | 39 |  | 70 | 30 | 40 | 50
Permalink |  | 7 | 7 |  | 50 | 50 | 0 | 50
Loading |  | 2 | 2 | Non testé | 40 | 60 | 20 | 50
Navigation | User navigation | 18 | 18 |  | 80 | 20 | 60 | 50
welcome screen |  | 38 | 38 |  | 80 | 20 | 60 | 50
Document preview | Preview document in Search | 44 | 44 |  | 60 | 30 | 30 | 45
Share in content Explorer |  | 45 | 45 |  | 50 | 40 | 10 | 45
Site explorer | Basic action | 235 | 235 |  | 60 | 30 | 30 | 45
Site explorer | Create node | 151 | 151 |  | 60 | 30 | 30 | 45
Basic portelets | Administration | 81 | 50 |  | 40 | 50 | 10 | 45
Content navigation |  | 3 | 3 | Non testé | 30 | 60 | 30 | 45
Chat conf |  | 33 | 33 | Non testé | 50 | 40 | 10 | 45
Search |  | 65 | 65 | Non testé | 30 | 50 | 20 | 40
Site explorer | CKeditor | 83 | 83 |  | 40 | 40 | 0 | 40
Regression |  | 25 | 25 |  | 50 | 30 | 20 | 40
Registration |  | 61 | 61 | Non testé | 0 | 80 | 80 | 40
Generic user popup |  | 79 | 79 | Non testé | 40 | 40 | 0 | 40
Accent caracters |  | 118 | 118 | Non testé | 40 | 40 | 0 | 40
Upload |  | 5 | 5 | Non testé | 40 | 40 | 0 | 40
|  | 4 | 4 |  | 20 | 20 | 0 | 40 |  |  | PLF | 452
Admin | Explorer | 62 | 0 |  | 40 | 30 | 10 | 35
Browsing preferences |  | 1 | 0 |  | 30 | 40 | 10 | 35
| File management View | 95 | 0 |  | 40 | 30 | 10 | 35
| Office test | 102 | 0 |  | 40 | 30 | 10 | 35
| Publish activities | 89 | 0 |  | 40 | 30 | 10 | 35
| Search | 39 | 0 |  | 40 | 30 | 10 | 35
WCM | Viewers | 143 | 0 |  | 40 | 30 | 10 | 35
Others | Mange page | 220 | 0 | Non testé | 40 | 30 | 10 | 35
Others | Hamburger menu | 23 | 0 | Non testé | 40 | 30 | 10 | 35
Others | others | 14 | 0 | Non testé | 40 | 30 | 10 | 35
Portal navigation | Edit | 218 | 0 | Non testé | 40 | 30 | 10 | 35
Portal navigation | Manage portal | 34 | 0 | Non testé | 40 | 30 | 10 | 35
Call button |  | 2 | 0 | Non testé | 30 | 40 | 10 | 30
Chat history |  | 24 | 0 | Non testé | 30 | 40 | 10 | 35
Chat responsive |  | 9 | 0 |  | 40 | 30 | 10 | 35
chat window |  | 218 | 0 | Non testé | 20 | 50 | 30 | 35
category |  | 17 | 0 |  | 40 | 20 | 20 | 30
Settings |  | 42 | 0 |  | 40 | 20 | 20 | 30
Admin | ECMS Admin conf | 95 | 0 |  | 30 | 30 | 0 | 30
Admin | Templates | 60 | 0 |  | 30 | 30 | 0 | 30
Basic portelets | Organisation | 92 | 0 |  | 40 | 20 | 20 | 30
Group navigation | Manage navigation | 15 | 0 |  | 40 | 20 | 20 | 30
Group navigation | Manage node | 56 | 0 |  | 40 | 20 | 20 | 30
Group navigation | Other node actions | 84 | 0 | Non testé | 30 | 30 | 0 | 30
Restricted page editor |  | 52 | 0 | Non testé | 0 | 60 | 60 | 30
Admin | Advanced | 78 | 0 |  | 30 | 20 | 10 | 25
WCM | Site admin toolbar | 2 | 0 |  | 20 | 30 | 10 | 25
Wicard membership |  | 66 | 0 |  | 10 | 40 | 30 | 25
Chat top navigation + management |  | 23 | 0 |  | 20 | 30 | 10 | 25
Mini chat |  | 32 | 0 |  | 20 | 30 | 10 | 25 |  |  | Mobile Test | Nbre test cases
|  | 61 | 0 |  | 20 | 30 | 10 | 25 |  |  | ECMS | 124
Admin | Repository | 51 | 0 | Non testé | 20 | 20 | 0 | 20
WCM | SEO | 50 | 0 |  | 10 | 30 | 20 | 20
WCM | Template pack | 8 | 0 |  | 10 | 30 | 20 | 20
Genric popup |  | 8 | 0 |  | 20 | 20 | 0 | 20
Chat Room user list |  | 115 | 0 |  | 20 | 20 | 0 | 20 |  |  | (MOB) gatein | 356
Desktop notif |  | 34 | 0 |  | 20 | 20 | 0 | 20 |  |  | Calendar | 348
|  | 191 | 0 |  | 10 | 30 | 20 | 20 |  |  | Chat | 451
View |  | 19 | 0 |  |  | 30 | 30 | 15
Global settings |  | 9 | 0 |  | 10 | 20 | 10 | 15
Dashboard |  | 25 | 0 |  | 0 | 20 | 20 | 10
Administration |  | 56 | 0 | Non testé | 30 | 60 | 30 | 0
Category |  | 82 | 0 | Non testé | 30 | 60 | 30 | 0
Ckeditor |  | 27 | 0 | Non testé | 40 | 60 | 20 | 0
Forum |  | 231 | 0 | Non testé | 40 | 60 | 20 | 0
Forum portlet settings |  | 17 | 0 | Non testé | 20 | 60 | 40 | 0
Others |  | 49 | 0 | Non testé | 10 | 60 | 50 | 0
Poll |  | 38 | 0 | Non testé | 50 | 60 | 10 | 0
Post |  | 68 | 0 | Non testé | 50 | 60 | 10 | 0
Private message |  | 14 | 0 | Non testé | 40 | 60 | 20 | 0
Topic |  | 113 | 0 | Non testé | 50 | 60 | 10 | 0
User settings |  | 29 | 0 | Non testé | 30 | 60 | 30 | 0
User mangement |  | 70 | 0 | Non testé | 30 | 60 | 30 | 0
Activities |  | 25 | 0 | Non testé | 40 | 40 | 0 | 0
Attachement |  | 14 | 0 | Non testé | 40 | 40 | 0 | 0
Basic action |  | 194 | 0 | Non testé | 40 | 40 | 0 | 0
Macro |  | 79 | 0 | Non testé | 30 | 40 | 10 | 0
Page info |  | 31 | 0 | Non testé | 60 | 40 | 20 | 0
Permessions |  | 44 | 0 | Non testé | 50 | 40 | 10 | 0
Search |  | 16 | 0 | Non testé | 40 | 40 | 0 | 0
Space switcher |  | 22 | 0 | Non testé | 30 | 40 | 10 | 0
Templates |  | 12 | 0 | Non testé | 60 | 40 | 20 | 0
Cluster | Advanced | 251 | 0 |  |  |  | 0 | 0
|  | 15909 | 8304 | 6547

## ENVT
| SERVER ENVIRONNEMENTS | [9 empty] | DESKTOP ENVIRONNEMENTS |  |  | MOBILE ENVIRONNEMENTS
| TOPOLOGIE | APPLICATION SERVER | OPERATING SYSTEM | JDK | DATABASE | SSO | DIRECTORY | MONGODB | ELASTICSEARCH | LIBRE OFFICE | BROWSER | DESKTOP RESOLUTION | SKIN | OS | PHONE | TABLET
| Standalone | Apache Tomcat 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | MySQL 5.7 | SAML v2.0 2.0 idp | eXo | MongoDB 4.0 | Elasticsearch 5.6.16 | LibreOffice 6.0 | Edge 44 | 1920x1080 | Enterprise skin | iOS 12 | iPhone 6 (750x1334) | iPad Air 2 (2048x1536)
| Cluster | Apache Tomcat 8.5 | Windows Server 2019 |  | PostgreSQL 11 |  | OpenLDAP 2.4 |  |  |  | Firefox ESR 68 |  | Default skin | Android 8.0 | Pixel (1080x1920) | Pixel C (2560x1800)
[7 empty] | Active Directory 2019 |  |  |  | Chrome 77
⬇ NEEDED ENVIRONMENTS FOR eXo 5.3 Test Campaign ⬇
TEST AUTO ( execution chaque semaine sur la nouvelle RCxx)
qa-auto-53-01 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | MySQL 5.7 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
qa-auto-53-02 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | PostgreSQL 11 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
TEST MANUELS
fqa01 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | MySQL 5.7 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
fqa02 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | PostgreSQL 11 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
fqa03 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | PostgreSQL 10 | - | OpenLDAP 2.4 | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
fqa04 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | MySQL 5.7 | - | Active Directory 2019 | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
fqa05 | Standalone | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | MySQL 5.7 | SAML v2.0 2.0 idp | OpenLDAP 2.4 / AD 2019 ?? | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
fqa06 | Cluster | TOMCAT 8.5 | Ubuntu 18.04 LTS | Open JDK 8 | PostgreSQL 11 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0
Local 1 | Standalone | TOMCAT 8.5 | Windows Server 2019 | Open JDK 8 | MySQL 5.7 | - | eXo | MongoDB 4.0 | Elastic Search 5.6.16 | LibreOffice 6.0

## Optimisation
Module | sub module |  | Story points | real | Historique tests 5.2.0 | BV guild architectes | BV guild analystes | Difference | BV moyen
Calendar | Activities |  | 73 | 73 |  | 60 | 40 | 20 | 50
| Basic action |  | 43 | 43 | Non testé | 50 | 60 | 10 | 55
| Manage calendar |  | 114 | 114 |  | 70 | 30 | 40 | 50
| Search |  | 65 | 65 | Non testé | 30 | 50 | 20 | 40
ECMS | Authentication |  | 4 | 4 |  | 50 | 50 | 0 | 50
| Copy of default folder |  | 7 | 7 |  | 50 | 60 | 10 | 55
| Document preview | Comment | 66 | 66 |  | 60 | 40 | 20 | 50
|  | Display area | 96 | 96 |  | 60 | 40 | 20 | 50
|  | ECMS rendering | 4 | 4 |  | 60 | 40 | 20 | 50
|  | Preview | 124 | 124 |  | 70 | 50 | 20 | 60
|  | Preview document in Search | 44 | 44 |  | 60 | 30 | 30 | 45
| Document Versionning |  | 116 | 116 |  | 50 | 60 | 10 | 55
| Share document |  | 84 | 84 |  | 60 | 40 | 20 | 50
| Share in content Explorer |  | 45 | 45 |  | 50 | 40 | 10 | 45
| Site explorer | Admin | 301 | 301 | Non testé | 40 | 60 | 20 | 50
|  | Basic action | 235 | 235 |  | 60 | 30 | 30 | 45
|  | CKeditor | 83 | 83 |  | 40 | 40 | 0 | 40
|  | Collaboration | 67 | 67 | Non testé | 40 | 60 | 20 | 50
|  | Create node | 151 | 151 |  | 60 | 30 | 30 | 45
|  | Info | 43 | 43 | Non testé | 40 | 60 | 20 | 50
|  | Open in office | 211 | 211 |  | 90 | 10 | 80 | 50
|  | Other check | 66 | 66 | Non testé | 40 | 60 | 20 | 50
|  | Publication | 20 | 20 |  | 60 | 40 | 20 | 50
GateIn | Autentificate |  | 39 | 39 |  | 70 | 30 | 40 | 50
| Basic portelets | Administration | 81 | 81 |  | 40 | 50 | 10 | 45
|  | Organisation | 92 | 92 |  | 40 | 40 | 0 | 40
| Regression |  | 25 | 25 |  | 50 | 30 | 20 | 40
| Registration |  | 61 | 61 | Non testé | 0 | 80 | 80 | 40
PLF | Permalink |  | 7 | 7 |  | 50 | 50 | 0 | 50
| Administration |  | 24 | 24 |  | 20 | 100 | 80 | 60
| Content navigation |  | 3 | 3 | Non testé | 30 | 60 | 30 | 45
| Disable user |  | 90 | 90 | Non testé | 40 | 70 | 30 | 55
| Generic user popup |  | 79 | 79 | Non testé | 40 | 40 | 0 | 40
| Loading |  | 2 | 2 | Non testé | 40 | 60 | 20 | 50
| Navigation | User navigation | 18 | 18 |  | 80 | 20 | 60 | 50
| Restricted page editor |  | 52 | 52 | Non testé | 0 | 60 | 60 | 30
| welcome screen |  | 38 | 38 |  | 80 | 20 | 60 | 50
Social | Space | Navigation mangement | 128 | 128 |  | 60 | 50 | 10 | 55
Wiki | Activities |  | 25 | 0 | Non testé | 60 | 40 | 20 | 50
| Attachement |  | 14 | 0 | Non testé | 60 | 40 | 20 | 50
| Basic action |  | 194 | 0 | Non testé | 60 | 40 | 20 | 50
| Page info |  | 31 | 0 | Non testé | 20 | 40 | 20 | 30
| Permessions |  | 44 | 0 | Non testé | 50 | 40 | 10 | 45
| Search |  | 16 | 0 | Non testé | 40 | 40 | 0 | 40
| Templates |  | 12 | 0 | Non testé | 20 | 40 | 20 | 30
Chat | Accent caracters |  | 118 | 118 | Non testé | 40 | 40 | 0 | 40
| Upload |  | 5 | 5 | Non testé | 40 | 40 | 0 | 40
| Chat conf |  | 33 | 33 | Non testé | 50 | 40 | 10 | 45
| Chat responsive |  | 9 | 0 |  | 40 | 30 | 10 | 35
| Mini chat |  | 32 | 0 |  | 20 | 30 | 10 | 25
| Desktop notif |  | 34 | 0 |  | 20 | 20 | 0 | 20
Task |  |  | 191 | 0 |  | 10 | 30 | 20 | 20
Web conf |  |  | 61 | 0 |  | 20 | 30 | 10 | 25